## light show 2025
Light Show 2025
Purchasing
Name | Subitems | Status | Timeline - Start | Timeline - End | Vendor | Seconds | Minutes | Link | Qty | Amt Each | Total | Remaining
Solder Seal Connectors |  | In Progress | 2025-09-01 | 2025-09-30 | Amazon |  | 0 | https://www.amazon.com/Connectors-Plustool-Self-Solder-Waterproof-Electrical/dp/B0B18NYX2S/ref=sr_1_16?dib=eyJ2IjoiMSJ9.nF2Lfd9NCcoZp2TyWjY5maddHVA4sTGUdbqBFpUKkP9VyDt6nR5pEFow2ioSQiUNMHciC919yqMAzqAcQRqmQkplGHYR9vMxuBHni_d8fpOLJAcVcY1AAaojYY8MOquQpaGlzmVlfPT_4Ji2BaSjfg.WOMKEH8dBkG1_hauGG3GCjVJdAJ12s_ncGY2bzPaKNU&dib_tag=se&keywords=solder%2Bseal&qid=1705295714&sr=8-16&th=1 | 1 | 36.99 | 36.99 | 36.99
Snow Machine |  | Not Started | 2025-11-01 | 2025-11-19 | Amazon |  | 0 |  |  |  | 0 | 0
|  |  | 2025-09-01 | 2025-11-19 |  |  | 0 |  |  |  | 36.99 | 36.99
Pixel Pushing
Name | Subitems | Status | Timeline - Start | Timeline - End | Vendor | Seconds | Minutes | Link | Qty | Amt Each | Total | Remaining
Tall Pixel Forest |  | In Progress | 2025-11-01 | 2025-11-22 | Holiday Coro |  | 0 |  |  |  | 0 | 0
|  |  | 2025-11-01 | 2025-11-22 |  |  | 0 |  |  |  | 0 | 0
Prepping & Wiring
Name | Subitems | Status | Timeline - Start | Timeline - End | Vendor | Seconds | Minutes | Link | Qty | Amt Each | Total | Remaining
Cut wires between pixel forest stakes |  | Not Started | 2025-11-01 | 2025-11-22 | N/A |  | 0 |  |  |  | 0 | 0
|  |  | 2025-11-01 | 2025-11-22 |  |  | 0 |  |  |  | 0 | 0
Sequencing
Name | Subitems | Status | Timeline - Start | Timeline - End | Vendor | Seconds | Minutes | Link | Qty | Amt Each | Total | Remaining
Christmas Songs | THX Intro,Let it Go,Wizards in Winter,Mary Did you Know,Cozy Little Christmas,Christmas Lights (Coldplay),Gobble Gobble,Merry Christmas (Elton John; Ed Sheeran),Over the River,All I want for Christmas is You,Red Christmas,Jingle Bells - Buble,Candy Cane Lane,Up on the Housetop (Reba),Jingle Bells - Kaskade, Soran,Do a Little Good,Snowman,Mad Russian Xmas,Rockin' Around the Christmas Tree (Brenda Lee),Frosty the Snowman - Original,Under the Tree - Kelly Clarkson,You Make it Feel Like Christmas,Blue Christmas,Defying Gravity,Grinch,Xmas Eve in Sarjevo,Xmas Vacay,It's the Most Wonderful Time of the Year,Hippo,Don't Know What Xmas Is,Christmas Tree Farm,Christmas Everyday,Xmas is Coming,Christmas isn't Cancelled,12 Days of Christmas - Straight no Chaser,The Greatest Show,Frosty the Snowman (Willie) | In Progress | 2025-05-01 | 2025-10-31 | N/A |  | 0 |  |  |  | 0 | 0
Subitems | Name | Floods | Tune To Matrix | Vocals | Forest | Matrix | Poles | Spinners | Status | Date Started | Date Finished | Priority | Speed | Instrumental
| THX Intro | [7 empty] | Done |  |  | Critical ⚠️️ | Medium | v
| Let it Go | [7 empty] | Done |  |  | Critical ⚠️️ | Medium
| Wizards in Winter | [7 empty] | Done |  |  | Critical ⚠️️ | Fast | v
| Mary Did you Know | [7 empty] | Done |  |  | Critical ⚠️️ | Slow
| Cozy Little Christmas | [7 empty] | Done |  |  | Critical ⚠️️ | Medium
| Christmas Lights (Coldplay) | [7 empty] | Done |  |  | Critical ⚠️️ | Slow
| Gobble Gobble | [7 empty] | Done |  |  | High | Medium
| Merry Christmas (Elton John; Ed Sheeran) | [7 empty] | Done |  |  | Critical ⚠️️ | Medium
| Over the River | [7 empty] | Done |  |  | High | Medium
| All I want for Christmas is You | [7 empty] | Done |  |  | Critical ⚠️️ | Medium
| Red Christmas | [7 empty] | Done |  |  | Low | Medium
| Jingle Bells - Buble | [7 empty] | Done |  |  | Medium | Slow
| Candy Cane Lane | [7 empty] | Done |  |  | Medium | Medium
| Up on the Housetop (Reba) | [7 empty] | Done |  |  | Medium | Medium
| Jingle Bells - Kaskade, Soran | [7 empty] | Done |  |  | Medium | Slow
| Do a Little Good | [7 empty] | Done |  |  | High | Medium
| Snowman | [7 empty] | Done |  |  | High | Slow
| Mad Russian Xmas | [7 empty] | Done |  |  | Critical ⚠️️ | Fast | v
| Rockin' Around the Christmas Tree (Brenda Lee) | [7 empty] | Done |  |  | Medium | Medium
| Frosty the Snowman - Original | [7 empty] | Done
| Under the Tree - Kelly Clarkson | [7 empty] | Done
| You Make it Feel Like Christmas | [7 empty] | Done |  |  | Medium | Medium
| Blue Christmas | [7 empty] | Done
| Defying Gravity | [7 empty] | Done |  |  | Medium | Medium
| Grinch | [7 empty] | Done |  |  | Medium | Medium
| Xmas Eve in Sarjevo | [7 empty] | Done |  |  | Critical ⚠️️ | Fast | v
| Xmas Vacay | [7 empty] | Done |  |  | Medium | Medium
| It's the Most Wonderful Time of the Year | [7 empty] | Done |  |  | Medium | Medium
| Hippo | [7 empty] | Done |  |  | Low | Medium
| Don't Know What Xmas Is | [7 empty] | Needs Update |  |  | Medium | Medium
| Christmas Tree Farm | [7 empty] | Under Consideration |  |  | Low | Medium
| Christmas Everyday | [7 empty] | Under Consideration |  |  | Medium | Medium
| Xmas is Coming | [7 empty] | Under Consideration |  |  | Low | Medium
| Christmas isn't Cancelled | [7 empty] | Under Consideration |  |  | Low | Medium
| 12 Days of Christmas - Straight no Chaser | [7 empty] | Under Consideration |  |  | Low | Medium
| The Greatest Show | [7 empty] | Under Consideration |  |  | Medium | Fast
| Frosty the Snowman (Willie) | [7 empty] | Under Consideration
|  |  | 2025-05-01 | 2025-10-31 |  |  | 0 |  |  |  | 0 | 0
Testing
Name | Subitems | Status | Timeline - Start | Timeline - End | Vendor | Seconds | Minutes | Link | Qty | Amt Each | Total | Remaining
Test Christmas Models | Megatree,Presents,Medium Canes,Small Canes,Singing Bulbs,Singing Tree,Mini Trees,Medium Flakes,Small Flakes,Mini Stars,Mega Star,AC Star,AC Tree | Not Started | 2025-11-01 | 2025-11-20 | N/A |  | 0 |  |  |  | 0 | 0
Subitems | Name | Floods | Tune To Matrix | Vocals | Forest | Matrix | Poles | Spinners | Status | Date Started | Date Finished | Priority | Speed | Instrumental
| Megatree | [7 empty] | Done
| Presents | [7 empty] | Not Started
| Medium Canes | [7 empty] | Not Started
| Small Canes | [7 empty] | Not Started
| Singing Bulbs | [7 empty] | Not Started
| Singing Tree | [7 empty] | Not Started
| Mini Trees | [7 empty] | Working on it
| Medium Flakes | [7 empty] | Done
| Small Flakes | [7 empty] | Not Started
| Mini Stars | [7 empty] | Not Started
| Mega Star | [7 empty] | Done
| AC Star | [7 empty] | Not Started
| AC Tree | [7 empty] | Done
|  |  | 2025-11-01 | 2025-11-20 |  |  | 0 |  |  |  | 0 | 0
Installing - Christmas
Name | Subitems | Status | Timeline - Start | Timeline - End | Vendor | Seconds | Minutes | Link | Qty | Amt Each | Total | Remaining
Running
Name | Subitems | Status | Timeline - Start | Timeline - End | Vendor | Seconds | Minutes | Link | Qty | Amt Each | Total | Remaining
Run Christmas Show |  | Not Started | 2025-11-23 | 2026-01-02 | N/A |  | 0 |  |  |  | 0 | 0
|  |  | 2025-11-23 | 2026-01-02 |  |  | 0 |  |  |  | 0 | 0
Research
Name | Subitems | Status | Timeline - Start | Timeline - End | Vendor | Seconds | Minutes | Link | Qty | Amt Each | Total | Remaining
Portable Hole Directions |  | Not Started | 2026-01-01 | 2026-01-31 | N/A |  | 0 | http://www.magicchristmas.org/uploads/3/4/6/9/34698654/portable_hole_ii_copy_2.pdf |  |  | 0 | 0
ASAP Pole Research |  | Not Started | 2026-01-01 | 2026-03-27 | N/A |  | 0 | http://www.magicchristmas.org/uploads/3/4/6/9/34698654/asap_sr_single_stage.pdf | 0 | 0 | 0 | 0
Tree Topper |  | Not Started | 2026-01-01 | 2026-01-24 | Boscoyo |  | 0 | https://boscoyostudio.com/products/steel-megatree-true-topper-46 | 1 | 115 | 115 | 115
Grommets (1/2" plus tool) |  | Not Started | 2026-01-01 | 2026-03-27 | Amazon |  | 0 | https://www.amazon.com/Grommet-Grommets-Handheld-Manual-Leather/dp/B0D3TCD3W3/ref=sr_1_2?crid=QLZVL01DKT4B&dib=eyJ2IjoiMSJ9.lOEbibSlDu3fj2SghwSuSp3w5rmG7IePKbJpRe5HTxeo4JYpB2txclaaxNiyZJtwptcC4T92UqR2BtkELizJ88jthLWe-IFQz_x3oGtI8UTiZ5Ke7IVOYktF9gRIHzHVgB_5xbkyt5zBwRTvE-mOTzlwl2kBOC-O9vMsqgcGmDy5dYJnwUzAF_vnvqG4CBBnkXygiSmoAAMhYP_2rMcGEnv8aDVSZJ2GJZtqekfxUti-2QjMdFK2SejTLq8BV4veY-Crd6ugPjtNoQfEj-UUCJJh13COWE3sWFndEUlEcTmzW-mn4DLkCgds2vi91wkYKNFobiX3FLthMZp9B-CdCilGFJsf-DSpWWztmp8_bR8j0ShBMfmxKDv9eFgU2v-tmmHHTPEO0J2mbIOZ3kc3vdop8M7CGmseIWNVotl0iNzxKnfYoK9MARJ4wSDr_lgE.9RCGeFLnkzzuIvP7xkKjgvgI3aTmJ-Wy4PURDxk6T9k&dib_tag=se&keywords=.5%2Binch%2Bgrommet&qid=1736093624&sprefix=5%2Binch%2Bgrommet%2Caps%2C165&sr=8-2&th=1 | 1 | 32 | 32 | 32
J Hooks (64) |  | Not Started | 2026-01-01 | 2026-03-28 | Gilbert Engineering |  | 0 | https://gilbertengineeringusa.com/products/t-hooks-for-mega-tree-topper?variant=44358531678520 | 1 | 60 | 60 | 60
|  |  | 2026-01-01 | 2026-03-28 |  |  | 0 |  |  |  | 207 | 207
Done
Name | Subitems | Status | Timeline - Start | Timeline - End | Vendor | Seconds | Minutes | Link | Qty | Amt Each | Total | Remaining
X Connect 5 Ft |  | Done | 2025-01-01 | 2025-02-28 | N/A |  | 0 | https://gilbertengineeringusa.com/products/extensions?variant=32253137616998 | 50 | 3 | 150 | $0
X Connect Females (20 AWG) |  | Done | 2025-01-01 | 2025-02-28 | N/A |  | 0 | https://www.holidaycoro.com/EasyPlug3-Female-Pigtail-xConnect-p/823-f.htm | 30 | 0.89 | 26.7 | $0
Smart Receiver |  | Done | 2025-01-01 | 2025-02-28 | N/A |  | 0 | https://www.holidaycoro.com/Ready2Run-4-8-SPI-Flex-Long-Range-SMART-Receiver-p/936.htm?CartID=8 | 1 | 199.9 | 199.9 | $0
X Connect Males (20 AWG) |  | Done | 2025-01-01 | 2025-02-28 | N/A |  | 0 | https://www.holidaycoro.com/EasyPlug3-Male-Pigtail-xConnect-p/823-m.htm | 30 | 0.89 | 26.7 | $0
X Connect 20 Ft |  | Done | 2025-01-01 | 2025-02-28 | N/A |  | 0 | https://gilbertengineeringusa.com/products/extensions?variant=32253137616998 | 10 | 8.5 | 85 | $0
X Connect 10 Ft |  | Done | 2025-01-01 | 2025-02-28 | N/A |  | 0 | https://gilbertengineeringusa.com/products/extensions?variant=32253137616998 | 20 | 5 | 100 | $0
X Connect Males (18 AWG) |  | Done | 2025-01-01 | 2025-02-28 | N/A |  | 0 | https://www.holidaycoro.com/EasyPlug3-Male-Pigtail-xConnect-p/723-m.htm | 20 | 1.04 | 20.8 | $0
X Connect Females (18 AWG) |  | Done | 2025-01-01 | 2025-02-28 | N/A |  | 0 | https://www.holidaycoro.com/EasyPlug3-Female-Pigtail-Dangle-xConnect-p/723-f.htm | 20 | 1.04 | 20.8 | $0
Pixels - 13,000 |  | Done | 2025-01-01 | 2025-02-28 | AliExpress |  | 0 | https://www.aliexpress.us/item/3256805086868911.html?spm=a2g0o.detail.pcDetailTopMoreOtherSeller.5.5fd7iwi1iwi1PH&gps-id=pcDetailTopMoreOtherSeller&scm=1007.40050.354490.0&scm_id=1007.40050.354490.0&scm-url=1007.40050.354490.0&pvid=2a737f17-02f4-404b-ba1d-c6aff7e36253&_t=gps-id:pcDetailTopMoreOtherSeller,scm-url:1007.40050.354490.0,pvid:2a737f17-02f4-404b-ba1d-c6aff7e36253,tpp_buckets:668%232846%238113%231998&pdp_npi=4%40dis%21USD%21696.00%21696.00%21%21%21696.00%21696.00%21%402101c5a417334976468468916e547e%2112000032441635375%21rec%21US%214290809228%21XZ&utparam-url=scene%3ApcDetailTopMoreOtherSeller%7Cquery_from%3A | 1 | 2157 | 2157 | $0
Matrix Clear Net |  | Done | 2025-04-01 | 2025-04-30 | Holiday Coro |  | 0 | https://www.holidaycoro.com/PixNode-Net-RGB-Pixel-Node-Mounting-Net-p/775.htm | 2 | 55.95 | 111.9 | $0
Pixaboost |  | Done | 2025-04-01 | 2025-04-30 | Holiday Coro |  | 0 | https://www.holidaycoro.com/Null-Pixel-Amplifier-F-Amp-Booster-PixaBoost-p/748.htm | 10 | 4.49 | 44.9 | $0
Spiders |  | Done | 2025-04-01 | 2025-04-30 | Holiday Coro |  | 0 | https://www.holidaycoro.com/Spider-p/4013-1.htm | 6 | 13.5 | 81 | $0
Pixel Forest Lights |  | Done | 2025-04-01 | 2025-04-30 | Holiday Coro |  | 0 | https://www.holidaycoro.com/Peace-Stake-5-Node-Pixel-Strings-with-Extensions-p/715-wp.htm | 100 | 4.49 | 449 | $0
Mini Stars |  | Done | 2025-04-01 | 2025-04-30 | Holiday Coro |  | 0 | https://www.holidaycoro.com/PixNode-Pixel-Mini-Tree-p/778.htm?CartID=25 | 8 | 3.49 | 27.92 | $0
Pixel Forest |  | Done | 2025-04-01 | 2025-04-30 | Holiday Coro |  | 0 | https://www.holidaycoro.com/Peace-Family-Slim-Pixel-Stakes-For-Nodes-p/270.htm | 100 | 1.69 | 169 | $0
Fuse Blocks |  | Done | 2025-04-01 | 2025-04-30 | Amazon |  | 0 | https://www.amazon.com/dp/B07GBV2MHN?ref_=ppx_hzsearch_conn_dt_b_fed_asin_title_2&th=1 | 4 | 15 | 60 | $0
Clickits |  | Done | 2025-04-01 | 2025-04-30 | Experience Lights |  | 0 | https://experiencelights.com/clickits-super-fast-pixel-splicing/ | 100 | 0.75 | 75 | $0
Spiders |  | Done | 2025-05-01 | 2025-05-31 | Holiday Coro |  | 0 | https://www.holidaycoro.com/Spider-p/4013-1.htm | 6 | 13.5 | 81 | $0
X Connect Ts |  | Done | 2025-06-01 | 2025-06-30 | Holiday Coro |  | 0 | https://www.holidaycoro.com/Three-Conductor-Tap-MFF-xConnect-EasyPlug3-p/730.htm | 20 | 3.99 | 79.8 | $0
Paint Control Boxes Black |  | Done | 2025-06-01 | 2025-07-31 | N/A |  | 0 |  |  |  | 0 | $0
3/4" Rings |  | Done |  |  | Holiday Coro |  | 0 | https://www.holidaycoro.com/product-p/655.htm?CartID=18 | 2 | 1.09 | 2.18 | $0
Power Supplies x 5 |  | Done | 2025-05-01 | 2025-05-31 | Holiday Coro |  | 0 | https://www.holidaycoro.com/Meanwell-LRS-350-12-12-Volt-350-Watt-Power-Supply-p/47.htm?CartID=2 | 5 | 38.94 | 194.7 | $0
Expansion Board x3 |  | Done | 2025-05-01 | 2025-05-31 | Holiday Coro |  | 0 | https://www.holidaycoro.com/Flex-Long-Range-Differential-Receiver-SMART-p/951-62.htm?CartID=19 | 3 | 45.95 | 137.85 | $0
Enclosure x2 |  | Done | 2025-05-01 | 2025-05-31 | Holiday Coro |  | 0 | https://www.holidaycoro.com/product-p/554.htm?CartID=10 | 2 | 37.03 | 74.06 | $0
Enclosure x1 |  | Done | 2025-05-01 | 2025-05-31 | Holiday Coro |  | 0 | https://www.holidaycoro.com/HC-2500-Holiday-Lighting-Enclosure-System-p/629.htm?CartID=22 | 1 | 60.27 | 60.27 | $0
Peace Steak Small x100 |  | Done | 2025-05-01 | 2025-05-31 | Holiday Coro |  | 0 | https://www.holidaycoro.com/Peace-Family-Slim-Pixel-Stakes-For-Nodes-p/270.htm?CartID=20 | 100 | 1.69 | 169 | $0
Receiver Adapter Plate x2 |  | Done | 2025-05-01 | 2025-05-31 | Holiday Coro |  | 0 | https://www.holidaycoro.com/Flex-Expansion-Long-Range-Receivers-to-CG-1500-p/642-kit1.htm?CartID=4 | 2 | 11.59 | 23.18 | $0
Power Supply Adapter Plate x2 |  | Done | 2025-05-01 | 2025-05-31 | Holiday Coro |  | 0 | https://www.holidaycoro.com/Dual-350w-Power-Supply-Mounting-Kit-p/639-kit1.htm?CartID=14 | 4 | 11.59 | 46.36 | $0
5 Amp Fuses |  | Done | 2025-05-01 | 2025-05-31 | Holiday Coro |  | 0 | https://www.holidaycoro.com/product-p/875.htm?CartID=1 | 16 | 0.29 | 4.64 | $0
X Connect 2 Ft |  | Done | 2025-05-01 | 2025-05-31 | Gilbert Engineering |  | 0 | https://gilbertengineeringusa.com/products/extensions?variant=39524788437094 | 50 | 1.5 | 75 | $0
Medium Flakes 3 |  | Done | 2025-05-01 | 2025-05-31 | Gilbert Engineering |  | 0 | https://gilbertengineeringusa.com/products/impression-flake-g?variant=31501534724198 | 2 | 50 | 100 | $0
GE Fuzion Spinner |  | Done | 2025-05-01 | 2025-05-31 | Gilbert Engineering |  | 0 | https://gilbertengineeringusa.com/products/fuzion?variant=44448587481400 | 1 | 75 | 75 | $0
Medium Flakes 2 |  | Done | 2025-05-01 | 2025-05-31 | Gilbert Engineering |  | 0 | https://gilbertengineeringusa.com/products/impression-flake-a?variant=31246236549222 | 2 | 50 | 100 | $0
2 Wire Low Voltage Wire |  | Done | 2025-07-01 | 2025-08-31 | Amazon |  | 0 | https://www.amazon.com/gp/product/B07Y6NJDQ4/ref=ppx_yo_dt_b_search_asin_title?ie=UTF8&psc=1 | 6 | 39.99 | 239.94 | $0
Small Canes |  | Done | 2025-05-01 | 2025-05-31 | Gilbert Engineering |  | 0 | https://gilbertengineeringusa.com/products/impression-candy-cane?_pos=1&_sid=8d993dd2d&_ss=r | 6 | 5 | 30 | $0
Singing Tree |  | Done | 2025-05-01 | 2025-05-31 | Gilbert Engineering |  | 0 | https://gilbertengineeringusa.com/products/impression-singing-tree-with-santa-hat-1?_pos=4&_sid=50ecf88d1&_ss=r | 1 | 165 | 165 | $0
Medium Flakes |  | Done | 2025-05-01 | 2025-05-31 | Gilbert Engineering |  | 0 | https://gilbertengineeringusa.com/products/impression-flake-f?variant=32230889324646 | 2 | 50 | 100 | $0
Bats |  | Done | 2025-05-01 | 2025-05-31 | Gilbert Engineering |  | 0 | https://gilbertengineeringusa.com/products/bat?_pos=5&_sid=2bcdf46c9&_ss=r | 5 | 7 | 35 | $0
Quick Clips (2 Wire) |  | Done | 2025-07-01 | 2025-07-31 | Amazon |  | 0 | https://www.amazon.com/dp/B07FJPMML6/ref=syn_sd_onsite_desktop_0?ie=UTF8&pd_rd_plhdr=t&aref=Y2Juw1nTje&th=1 | 10 | 11.53 | 115.3 | $0
Add Fuse Box to 5 Boxes |  | Done | 2025-04-01 | 2025-04-30 | Amazon |  | 0 |  |  |  | 0 | $0
Bats |  | Done | 2025-06-01 | 2025-06-30 | Gilbert Engineering |  | 0 | https://gilbertengineeringusa.com/products/bat?_pos=5&_sid=2bcdf46c9&_ss=r | 5 | 7 | 35 | $0
GE Fuzion Spinner |  | Done | 2025-05-01 | 2025-05-30 | Gilbert Engineering |  | 0 | https://gilbertengineeringusa.com/products/space-odyssey?_pos=2&_sid=e81010ede&_ss=r | 1 | 60 | 60 | $0
Redo Arches w/ 12v |  | Done | 2025-05-01 | 2025-05-30 | N/A |  | 0 |  |  |  | 0 | $0
Redo Mini Trees w/ 12v |  | Done | 2025-05-01 | 2025-05-30 | N/A |  | 0 |  |  |  | 0 | $0
Pixel Posts |  | Done | 2025-06-01 | 2025-07-31 | N/A |  | 0 |  |  |  | 0 | $0
Matrix |  | Done | 2025-04-13 | 2025-08-10 | Holiday Coro |  | 0 | https://www.holidaycoro.com/PixNode-Net-RGB-Pixel-Node-Mounting-Net-p/775.htm | 2 | 55.95 | 111.9 | $0
Halloween Songs | Spooky Scary Skeletons,This is Halloween,Thriller Remix,Separate Ways,Save Tonight,Purple People Eater -Dubstep,Ghostbusters - I'm Not Afraid,Monster Mash,E.T.,Haunted Mansion Intro,Defying Gravity,Believer,Paint it Black (Wednesday) - Transition,Carousel (Melanie Martinez),Halloween Theme (Transition),Abracadabra - Lady Gaga,Shadow (Livingston),I Put a Spell on You,You Make me Feel Like It's Halloween,Darkside (Neoni),It Remix,Your Idol (Kpop Demon Hunters) | Done | 2025-01-01 | 2025-07-31 | N/A |  | 0 |  |  |  | 0 | $0
Subitems | Name | Floods | Tune To Matrix | Vocals | Forest | Matrix | Poles | Spinners | Status | Date Started | Date Finished | Priority | Speed | Instrumental
| Spooky Scary Skeletons | v | v | v | v | v | v | v | Done |  |  | Medium | Fast
| This is Halloween | v | v | v | v | v | v | v | Done |  | 2025-01-22 | Critical ⚠️️ | Medium
| Thriller Remix | v | v | v | v | v | v | v | Done |  |  | Medium | Medium
| Separate Ways | v | v | v | v | v | v | v | Done |  | 2025-01-16 | Critical ⚠️️ | Slow
| Save Tonight | v | v | v | v | v | v | v | Done |  |  | Medium | Slow
| Purple People Eater -Dubstep | v | v | v | v | v | v | v | Done |  |  | Medium | Fast
| Ghostbusters - I'm Not Afraid | v | v | v | v | v | v | v | Done |  |  | Medium | Medium
| Monster Mash | v | v | v | v | v | v | v | Done |  |  | Medium | Medium
| E.T. | v | v | v | v | v | v | v | Done |  |  | High | Fast
| Haunted Mansion Intro | v | v | v | v | v | v | v | Done |  |  | Critical ⚠️️ | Medium
| Defying Gravity | v | v | v | v | v | v | v | Done |  |  | High | Medium
| Believer | v | v | v | v | v | v | v | Done |  |  | Medium | Fast
| Paint it Black (Wednesday) - Transition | v | v | v | v | v | v | v | Done |  |  | Medium | Slow | v
| Carousel (Melanie Martinez) | v | v | v | v | v | v | v | Done |  |  | High | Medium
| Halloween Theme (Transition) | v | v | v | v | v | v | v | Done |  |  | Medium | Slow | v
| Abracadabra - Lady Gaga | v | v | v | v | v | v | v | Done |  | 2025-04-05 | Medium | Medium
| Shadow (Livingston) | v | v | v | v | v | v | v | Done | 2025-04-09 | 2025-04-21 | Medium | Medium
| I Put a Spell on You | v | v | v | v | v | v | v | Done |  |  | Medium | Medium
| You Make me Feel Like It's Halloween | v | v | v | v | v | v | v | Done |  |  | Medium | Fast
| Darkside (Neoni) | v | v | v | v | v | v | v | Done |  |  | Medium | Medium
| It Remix | v | v | v | v | v | v | v | Done |  |  | Medium | Medium | v
| Your Idol (Kpop Demon Hunters) | v | v | v | v | v | v | v | Done
Fireworks |  | Done | 2025-08-01 | 2025-08-31 | N/A |  | 0 |  |  |  | 0 | $0
Pixel Forest |  | Done | 2025-08-01 | 2025-08-31 | Holiday Coro |  | 0 | https://www.holidaycoro.com/Peace-Stake-5-Node-Pixel-Strings-with-Extensions-p/715-wp.htm | 100 | 4.49 | 449 | $0
Metal Conduit for Mounting |  | Done | 2025-08-01 | 2025-08-31 | Home Depot |  | 0 | https://www.homedepot.com/p/1-2-in-x-10-ft-Electrical-Metallic-Tubing-EMT-Conduit-0550010000/202068039 | 6 | 5.98 | 35.88 | $0
2" Pipe |  | Done | 2025-08-01 | 2025-08-31 | Home Depot |  | 0 | https://www.homedepot.com/p/2-in-x-10-ft-Rigid-Metal-Conduit-8531-108HD/330387473?MERCH=REC-_-rv_gm_pip_rr-_-n/a-_-6-_-n/a-_-n/a-_-n/a-_-n/a-_-n/a |  |  | 0 | $0
EMT - 3/4" for Box Mounting |  | Done | 2025-08-01 | 2025-08-31 | Home Depot |  | 0 |  |  |  | 0 | $0
Flange for Top of Pole |  | Done | 2025-08-01 | 2025-08-31 | Home Depot |  | 0 | https://www.homedepot.com/p/Southland-2-in-Galvanized-Malleable-Iron-Floor-Flange-Fitting-511-608HN/100175260 |  |  | 0 | $0
PVC Pipes (3/4 inch for Arches) |  | Done | 2025-08-01 | 2025-08-31 | Home Depot |  | 0 | https://www.homedepot.com/p/Charlotte-Pipe-3-4-in-x-10-ft-PVC-Schedule-40-Pressure-Plain-End-Pipe-PVC-04007-0600/100348472 | 8 | 6.29 | 50.32 | $0
Cattle Panel for Fireworks |  | Done | 2025-08-01 | 2025-08-31 | Home Depot |  | 0 |  |  |  | 0 | $0
EMT 1/2" for Supports |  | Done | 2025-08-01 | 2025-08-31 | Home Depot |  | 0 |  |  |  | 0 | $0
4 Rebar |  | Done | 2025-08-01 | 2025-08-31 | N/A |  | 0 |  |  |  | 0 | $0
Tune To Matrix |  | Done | 2025-08-01 | 2025-08-31 | Holiday Coro |  | 0 |  |  |  | 0 | $0
Mount Fireworks to Cattle Panel |  | Done | 2025-08-01 | 2025-08-31 | N/A |  | 0 |  |  |  | 0 | $0
Mounting Hardware for Bats |  | Done | 2025-08-01 | 2025-08-31 | N/A |  | 0 |  |  |  | 0 | $0
Cut EMT |  | Done | 2025-08-01 | 2025-08-31 | N/A |  | 0 |  |  |  | 0 | $0
Label All Wires from Boxes |  | Done |  |  | N/A |  | 0 |  |  |  | 0 | $0
Test House Layouts | Office,Guest Room,Garage,Tower,Guest Bath,Avery,Ellis,Entrance Arch | Done | 2025-09-01 | 2025-09-30 | N/A |  | 0 |  |  |  | 0 | $0
Subitems | Name | Floods | Tune To Matrix | Vocals | Forest | Matrix | Poles | Spinners | Status | Date Started | Date Finished | Priority | Speed | Instrumental
| Office | [7 empty] | Done
| Guest Room | [7 empty] | Done
| Garage | [7 empty] | Done
| Tower | [7 empty] | Done
| Guest Bath | [7 empty] | Done
| Avery | [7 empty] | Done
| Ellis | [7 empty] | Done
| Entrance Arch | [7 empty] | Done
Test Halloween Models | Bats,Tombstones,Spiders,Pixel Posts,Matrix,Mini Trees,Fuzion,Showstoppers,Arches,Fireworks,Pixel Forest,Tune To Matrix,Singing Pumpkin,Mini Pumpkins,Floods | Done | 2025-05-01 | 2025-08-31 | N/A |  | 0 |  |  |  | 0 | $0
Subitems | Name | Floods | Tune To Matrix | Vocals | Forest | Matrix | Poles | Spinners | Status | Date Started | Date Finished | Priority | Speed | Instrumental
| Bats | [7 empty] | Done
| Tombstones | [7 empty] | Done
| Spiders | [7 empty] | Done
| Pixel Posts | [7 empty] | Done
| Matrix | [7 empty] | Done
| Mini Trees | [7 empty] | Done
| Fuzion | [7 empty] | Done
| Showstoppers | [7 empty] | Done
| Arches | [7 empty] | Done
| Fireworks | [7 empty] | Done
| Pixel Forest | [7 empty] | Done
| Tune To Matrix | [7 empty] | Done
| Singing Pumpkin | [7 empty] | Done
| Mini Pumpkins | [7 empty] | Done
| Floods | [7 empty] | Done
Mounting Hardware for Spiders |  | Done | 2025-09-01 | 2025-09-30 | N/A |  | 0 |  |  |  | 0 | $0
Spiders |  | Done | 2025-10-03 | 2025-10-05 | N/A |  | 0 | https://www.holidaycoro.com/Spider-p/4013-1.htm | 6 | 13.5 | 81 | $0
Fireworks |  | Done | 2025-10-03 | 2025-10-04 | N/A |  | 0 |  |  |  | 0 | $0
Pumpkin |  | Done | 2025-10-03 | 2025-10-05 | N/A |  | 0 |  |  |  | 0 | $0
Rent a Lift |  | Done | 2025-10-03 | 2025-10-03 | N/A |  | 0 |  |  |  | 0 | $0
House | Office,Guest Room,Guest Bath,Garage,Tower,Avery,Ellis | Done | 2025-10-03 | 2025-10-05 | N/A |  | 0 |  |  |  | 0 | $0
Subitems | Name | Floods | Tune To Matrix | Vocals | Forest | Matrix | Poles | Spinners | Status | Date Started | Date Finished | Priority | Speed | Instrumental
| Office | [7 empty] | Done
| Guest Room | [7 empty] | Done
| Guest Bath | [7 empty] | Done
| Garage | [7 empty] | Done
| Tower | [7 empty] | Done
| Avery | [7 empty] | Done
| Ellis | [7 empty] | Done
Arches | Zip to pipes,Install in Yard | Done | 2025-10-03 | 2025-10-05 | N/A |  | 0 |  |  |  | 0 | $0
Subitems | Name | Floods | Tune To Matrix | Vocals | Forest | Matrix | Poles | Spinners | Status | Date Started | Date Finished | Priority | Speed | Instrumental
| Zip to pipes | [7 empty] | Not Started
| Install in Yard | [7 empty] | Not Started
Mini Pumpkins |  | Done | 2025-10-03 | 2025-10-05 | N/A |  | 0 |  |  |  | 0 | $0
Matrix |  | Done | 2025-10-03 | 2025-10-05 | N/A |  | 0 | https://www.holidaycoro.com/PixNode-Net-RGB-Pixel-Node-Mounting-Net-p/775.htm | 2 | 55.95 | 111.9 | $0
Spinners |  | Done | 2025-10-03 | 2025-10-05 | N/A |  | 0 |  |  |  | 0 | $0
Fuzion Spinner | Prep office window cables for spinner | Done | 2025-10-03 | 2025-10-05 | N/A |  | 0 | https://gilbertengineeringusa.com/products/space-odyssey?_pos=2&_sid=e81010ede&_ss=r | 1 | 60 | 60 | $0
Subitems | Name | Floods | Tune To Matrix | Vocals | Forest | Matrix | Poles | Spinners | Status | Date Started | Date Finished | Priority | Speed | Instrumental
| Prep office window cables for spinner | [7 empty] | Not Started
Pixel Forest |  | Done | 2025-10-03 | 2025-10-05 | N/A |  | 0 | https://www.holidaycoro.com/Peace-Stake-5-Node-Pixel-Strings-with-Extensions-p/715-wp.htm | 100 | 4.49 | 449 | $0
Bats |  | Done | 2025-10-03 | 2025-10-05 | N/A |  | 0 | https://gilbertengineeringusa.com/products/bat?_pos=5&_sid=2bcdf46c9&_ss=r | 5 | 7 | 35 | $0
Tune To Matrix |  | Done | 2025-10-03 | 2025-10-04 | N/A |  | 0 |  |  |  | 0 | $0
Pixel Poles |  | Done | 2025-10-03 | 2025-10-05 | N/A |  | 0 |  |  |  | 0 | $0
Tombstones |  | Done |  |  | N/A |  | 0 |  |  |  | 0 | $0
Paint Cords House Color |  | Done | 2025-09-01 | 2025-09-30 | N/A |  | 0 |  |  |  | 0 | $0
Fog Machine |  | Done | 2025-09-01 | 2025-09-30 | Amazon |  | 0 |  |  |  | 0 | $0
Mount Boxes to 1" EMT |  | Done | 2025-09-01 | 2025-09-30 | N/A |  | 0 |  |  |  | 0 | $0
Pixel Pole Bottom/Top |  | Done |  |  | N/A |  | 0 | https://boscoyostudio.com/products/mega-tree-topper-12-24?_pos=2&_sid=c8666d34a&_ss=r | 10 | 20 | 200 | $0
Mini Stars |  | Done | 2025-10-01 | 2025-10-30 | Holiday Coro |  | 0 |  |  |  | 0 | $0
Small Canes |  | Done | 2025-10-01 | 2025-10-30 | Gilbert Engineering |  | 0 | https://gilbertengineeringusa.com/products/impression-candy-cane?_pos=1&_sid=8d993dd2d&_ss=r | 8 | 5 | 40 | $0
Singing Tree |  | Done | 2025-10-01 | 2025-10-30 | Gilbert Engineering |  | 0 | https://gilbertengineeringusa.com/products/singing-tree-with-santa-hat?_pos=23&_sid=b06119fbf&_ss=r | 1 | 85 | 85 | $0
Medium Flakes |  | Done | 2025-10-01 | 2025-10-30 | Gilbert Engineering |  | 0 | https://gilbertengineeringusa.com/products/impression-flake-f?variant=32230889324646 | 2 | 50 | 100 | $0
AC Star |  | Done |  |  | N/A |  | 0 |  |  |  | 0 | $0
Small Snowflakes |  | Done | 2025-10-01 | 2025-10-31 | Holiday Coro |  | 0 |  |  |  | 0 | $0
New Presents |  | Done | 2025-10-01 | 2025-10-30 | Holiday Coro |  | 0 |  |  |  | 0 | $0
Mount small flakes to wire mesh and mount on 1/2" EMT |  | Done | 2025-11-01 | 2025-11-22 | N/A |  | 0 |  |  |  | 0 | $0
Ensure Pixel Poles are elevated on 1/2" EMT |  | Done | 2025-11-01 | 2025-11-22 | N/A |  | 0 |  |  |  | 0 | $0
Double check wiring on Pixel Poles - clean up |  | Done | 2025-11-01 | 2025-11-22 | N/A |  | 0 |  |  |  | 0 | $0
Update Hinks Pix Box w/ 8 more ports |  | Done |  |  | N/A |  | 0 |  |  |  | 0 | $0
Candy Canes |  | Done | 2025-11-21 | 2025-11-23 | N/A |  | 0 |  |  |  | 0 | $0
Presents |  | Done | 2025-11-21 | 2025-11-23 | N/A |  | 0 |  |  |  | 0 | $0
Mega Tree |  | Done | 2025-11-21 | 2025-11-23 | N/A |  | 0 |  |  |  | 0 | $0
Singing Bulbs |  | Done | 2025-11-21 | 2025-11-23 | N/A |  | 0 |  |  |  | 0 | $0
Small Flakes |  | Done | 2025-11-21 | 2025-11-23 | N/A |  | 0 |  |  |  | 0 | $0
Singing Tree |  | Done | 2025-11-21 | 2025-11-23 | N/A |  | 0 | https://gilbertengineeringusa.com/products/singing-tree-with-santa-hat?_pos=23&_sid=b06119fbf&_ss=r | 1 | 85 | 85 | $0
Medium Flakes |  | Done | 2025-11-21 | 2025-11-23 | N/A |  | 0 | https://gilbertengineeringusa.com/products/impression-flake-f?variant=32230889324646 | 2 | 50 | 100 | $0
Small Canes |  | Done | 2025-11-21 | 2025-11-23 | N/A |  | 0 | https://gilbertengineeringusa.com/products/impression-candy-cane?_pos=1&_sid=8d993dd2d&_ss=r | 8 | 5 | 40 | $0
AC Tree |  | Done |  |  | N/A |  | 0 |  |  |  | 0 | $0
Run Halloween Show |  | Done | 2025-10-05 | 2025-10-31 | N/A |  | 0 |  |  |  | 0 | $0
|  |  | 2025-01-01 | 2025-11-23 |  |  | 0 |  |  |  | 7842.9 | null
Next Year Songs
Name | Subitems | Status | Timeline - Start | Timeline - End | Vendor | Seconds | Minutes | Link | Qty | Amt Each | Total | Remaining
Halloween Songs | Saw Outtro,Red (Descendants),Enter Sandman,Dragula,Beetlejuice Intro,Day-Oh,Stranger Things Intro,One Way or Another - Hocus Pocus,Thunderstruck,Cirice,Hells Bells,Pink Pony Club,Harry Potter Theme (Transition),Wednesday Medley,Paint it Black (Bishop Briggs),Bad Guy (Billie Eilish),Bloody Mary (Lady Gaga),Ways to Be Wicked,Rotten to the Core | Not Started |  |  | N/A |  | 0 |  |  |  | 0 | 0
Subitems | Name | Floods | Tune To Matrix | Vocals | Forest | Matrix | Poles | Spinners | Status | Date Started | Date Finished | Priority | Speed | Instrumental
| Saw Outtro | [7 empty] | Under Consideration |  |  | Low | Medium | v
| Red (Descendants) | [7 empty] | Under Consideration |  |  | Medium | Fast
| Enter Sandman | [7 empty] | Under Consideration |  |  | Medium | Fast
| Dragula | [7 empty] | Under Consideration |  |  | Medium | Fast
| Beetlejuice Intro | [7 empty] | Under Consideration |  |  | Medium | Medium
| Day-Oh | [7 empty] | Under Consideration |  |  | Medium | Slow
| Stranger Things Intro | [7 empty] | Under Consideration |  |  | Medium | Slow
| One Way or Another - Hocus Pocus | [7 empty] | Under Consideration |  |  | Medium | Medium
| Thunderstruck | [7 empty] | Under Consideration |  |  | Low | Fast
| Cirice | [7 empty] | Under Consideration |  |  | Low | Medium
| Hells Bells | [7 empty] | Under Consideration |  |  | Low | Fast
| Pink Pony Club | [7 empty] | Under Consideration |  |  | Low | Fast
| Harry Potter Theme (Transition) | [7 empty] | Under Consideration |  |  | Medium | Medium
| Wednesday Medley | [7 empty] | Under Consideration |  |  | Low | Medium
| Paint it Black (Bishop Briggs) | [7 empty] | Under Consideration |  |  | Medium | Slow
| Bad Guy (Billie Eilish) | [7 empty] | Under Consideration |  |  | Low | Slow
| Bloody Mary (Lady Gaga) | [7 empty] | Under Consideration |  |  | Medium | Medium
| Ways to Be Wicked | [7 empty] | Under Consideration |  |  | Medium | Fast
| Rotten to the Core | [7 empty] | Under Consideration
Christmas Songs | What's This,Here it is Christmastime (Guardians) | Not Started |  |  | N/A |  | 0 |  |  |  | 0 | 0
Subitems | Name | Floods | Tune To Matrix | Vocals | Forest | Matrix | Poles | Spinners | Status | Date Started | Date Finished | Priority | Speed | Instrumental
| What's This | [7 empty] | Under Consideration |  |  | Low | Medium
| Here it is Christmastime (Guardians) | [7 empty] | Under Consideration |  |  | Low | Medium
[7 empty] | 0 |  |  |  | 0 | 0